## Slide 2: General Organization
Notes: Lloyd

## Slide 3: Status Monitoring
Internal
  Work Breakdown Structure
  Status Reports
  Immediate Task Status Reporting
  Scheduled Meetings
External
  Team Status Reports
  Team Status Update Presentations
Notes: Lloyd

## Slide 4: Roles and Responsibilities
Team Members | Responsibilities
Chudamani Aryal | Project Manager, Project planner, Integration lead, Schedule
Tyler Buchanan | Change manager, Collaborator, Document Manager
Jefferson White | Presentation, Risk Manager
Lloyd Bond | Procurement Manager, Quality Manager, Meeting scribe
Notes: Lloyd

## Slide 5: Project Constraints & Assumptions
Constraints
  Time Limit
  4-person team
  Limited Budget
Assumptions
  Weather
  Maintenance
  Power Availability
Notes: Lloyd

## Slide 6: Schedule & Cost Estimates
Checkpoints
  Requirement Review Gate 24 July, 2012
  Architectural Design Gate September, 2012
  Detailed Design Gate October, 2012
  Test Plan Gate November, 2012
  Prototype Delivery December 2012
Cost Estimates
  $ 800 Budget
Notes: Lloyd

## Slide 7: Scope Statement
Notes: Lloyd

## Slide 8
The goal of this project is to determine if early detection of inadequate ride or smoothness in Portland cement concrete (PCC) pavements can be determined and, if so, identify the appropriate correction device or procedures that can be applied before the concrete has hardened.
The upgrade will feature
PIC Microcontroller instead of an Embedded PC
GPS location tracking
More Friendly UI
Improved platform (floating capability, light weight, better mechanical design)
More tolerant components for extreme weather conditions applicable to laying concrete
Notes: Lloyd

## Slide 9: Rear view of a typical paver
Notes: Lloyd

## Slide 10: Quality Management Plan
Notes: Lloyd

## Slide 11: Overview
Component Testing
Integration Testing
Formal & Informal Test Plans
Access to Previous Test Results
Notes: Lloyd

## Slide 12: Roles and Responsibilities
Role | Responsibilities | Assigned Personnel
Quality manager | Inquire about testing progress/issues of completed components Help generate formal and informal test plans Track component testing results for future reference Report any findings and keep the group apprised of known bugs and flaws Ensure product development continues to take into account the acceptance criteria Assess priority of findings and allocate resources to address as necessary | Lloyd Bond
Notes: Lloyd

## Slide 13: Roles and Responsibilities
Role | Responsibilities | Assigned Personnel
Hardware, Software, Platform Developers | Generate informal test plans with Quality Manager’s assistance as necessary Test individual components before submission as complete Inform Quality Manager of testing generalities and any issues encountered | Team Members
Test Engineers | Follow formal test plans Perform integration testing Inform Quality Manager of results of testing and any issues encountered | Team Members
Notes: Lloyd

## Slide 14: Procurement Management Plan
Notes: Lloyd

## Slide 15: Roles and Responsibilities
Role | Responsibilities | Assigned Personnel
Project Sponsor | Make purchasing approvals | Roger Walker
Team Supervisor | Make purchasing approvals | Michael O’Dell
Procurement Manager | Work with Lead Architect to identify project procurement needs Perform procurement cost analysis Obtain procurement approval Track purchase orders Report completed purchases | Lloyd Bond
Notes: Lloyd

## Slide 16: Roles and Responsibilities
Role | Responsibilities | Assigned Personnel
Integration Lead | Work with Procurement Manager, Hardware Architect, Software Architect, Platform Architect to identify purchasing needs | Chudamani Aryal
Team Members | Perform procurement identification as necessary according to role | Chudamani Aryal, Tyler Buchanan, Jefferson White, Lloyd Bond
Notes: Lloyd

## Slide 17: Cost Management Plan
Notes: CM

## Slide 18
Labor Management
  Breakdown of Schedule
  Work Allocation
  Team Meetings
  Internal Deadlines
Material Management
  Approval of Purchase Order
  Response to Cost Variances
  Use of Re-Useable Materials
Notes: CM

## Slide 19: Work Breakdown Structure
Notes: CM

## Slide 20: Phase 1
SRS
Project Charter
Team Meetings
Sponsor Meetings
R&D
Notes: CM

## Slide 21: Phase 2
ADS
DDS
Test Plan
Implementation
Team Meetings
Sponsor Meetings
Notes: CM

## Slide 22: MS Project Sample
Notes: CM

## Slide 23: Earned Value Management
Notes: Jeff

## Slide 24: Measurement
Budgeted Cost of Work Scheduled (BCWS)
Actual Cost of Work Performed (ACWP)
Budgeted Cost of Work Performed (BCWP)
Notes: Jeff

## Slide 25: Reporting
Cost Performance Index
CPI = BCWP/ACWP
Schedule Performance Index
SPI = BCWP/BCWS
Analysis
CPI > 1.0 = exceptional performance
CPI < 1.0 = poor performance
Similar for SPI
Notes: Jeff

## Slide 26: Change Management Plan
Notes: Jeff

## Slide 27: Roles and Responsibilities
Project Sponsor
Project Manager
Change Manager
Project Team
Notes: Jeff

## Slide 28: Review & Approval Process
Analysis of Impact
Discussion
Approval
Plan of Action
Notes: Jeff

## Slide 29: Risk Management Plan
Notes: Jeff

## Slide 30: Roles and Responsibilities
Project Sponsor
Project Manager
Risk Manager
Project Team
Notes: Jeff

## Slide 31: Risk Management Steps
Source: Mr. Mike O’Dell
Notes: Jeff

## Slide 32: Risk Analysis Sample
Name | Priority(1-5) | Likelihood(%) | Size of loss (weeks) | Severity (likelihood x size of loss)
Burnout | 1-2 | 95 | 2 | 1.9
Personnel Availability | 4 | 80 | 2 | 1.6
Doesn't float | 1 | 40 | 3 | 1.2
Extreme Temp Failure | 1 | 40 | 3 | 1.2
Project Failure | 1 | 30 | 4 | 1.2
Sponsor Availability | 5 | 50 | 2 | 1
Frame Resilience | 4 | 30 | 2 | 0.6
Lack of Buy-in | 5 | 20 | 3 | 0.6
Notes: Jeff

## Slide 33: Scope Management Plan
The scope of this project will be defined by the baseline requirement specification
Any possible changes to the scope will be discussed with the team and project sponsor
Notes: Tyler

## Slide 34: Communications Plan
Notes: Tyler

## Slide 35: Internal Communications
Meetings
Phone
Emails
GitHub
Notes: Tyler

## Slide 36: External Communications
Includes Sponsor and Team Supervisor
  Emails
  Personal Meetings
Notes: Tyler

## Slide 37: Project Closeout Report
Notes: Tyler

## Slide 38: Administrative Closure
Objectives Met
Archiving Project Artifacts
Lessons Learned Sessions
Post Review
Final Customer Acceptance
Final Project Performance Report
Notes: Tyler